## Summary
Config status
Overall progress | 0% | [7 empty] | 05 - eCase config completed | Total
Count of #
Country | 01 - Yet to start | 02 - In progress | 03 - Under review | 04 - Sent to eCase | 05 - eCase config completed | 06 - Ready for QA | 07 - Blocked | Total | 0 | 9
AU | [5 empty] | 3 | 3 | 6 | Config
BB | [5 empty] | 2 |  | 2 | 01 - Yet to start
BO | [5 empty] | 2 |  | 2 | 02 - In progress
CL | 1 |  | 1 | 2 | 1 |  | 3 | 8 | 03 - Under review
CR | [5 empty] | 5 |  | 5 | 04 - Sent to eCase
DO | 1 |  | 1 | 3 | 1 | 10 |  | 16 | 05 - eCase config completed
GB | [6 empty] | 1 | 1 | 06 - Ready for QA
HU | [5 empty] | 1 |  | 1 | 07 - Blocked
ID | [5 empty] | 1 |  | 1
IL | [5 empty] | 2 |  | 2
JO | [5 empty] | 5 |  | 5
MA |  |  |  |  | 2 | 3 |  | 5
MM | 1 |  |  |  | 2 |  |  | 3
NZ | 1 |  |  |  |  | 1 |  | 2
SE | [5 empty] | 5 |  | 5
SV | [6 empty] | 2 | 2
TR | 2 |  |  |  |  | 2 |  | 4
VE | 2 |  |  |  |  | 2 |  | 4
XC | 6 |  |  |  |  | 3 | 1 | 10
GR | 4 | 1 |  |  |  | 5 |  | 10
AT |  | 1 | [5 empty] | 1
Total | 18 | 2 | 2 | 5 | 6 | 52 | 10 | 95
QA Status
Executed | 11.11%
Pass rate | 11.11%
Count of #
Country | 01 - Yet to start | 02 - Fail | 03 - Func. Testing completed | 04 - Blocked | Total | UAT Status |  |  | 02 - Fail | 03 - Func. Testing completed | Total
AU |  |  | 3 | 3 | 6 | Ready for UAT |  |  | 0 | 1 | 9
BB |  |  | 2 |  | 2 | Ready for UAT |  |  | QA
BO |  |  | 2 |  | 2 | Ready for UAT |  |  | 01 - Yet to start
CL | 7 | 1 |  |  | 8 | Ready for UAT |  |  | 02 - Fail
CR | 1 |  | 4 |  | 5 | Ready for UAT |  |  | 03 - Func. Testing completed
DO | 12 |  | 4 |  | 16 | Ready for UAT |  |  | 04 - Blocked
GB |  |  |  | 1 | 1 | Ready for UAT
HU |  |  | 1 |  | 1 | Ready for UAT
ID |  |  | 1 |  | 1 | Ready for UAT
IL | 1 |  | 1 |  | 2 | Ready for UAT
JO | 5 |  |  |  | 5 | Ready for UAT
MA | 2 | 3 |  |  | 5 | Ready for UAT
MM | 2 |  |  | 1 | 3 | Ready for UAT
NZ |  |  | 1 | 1 | 2 | Ready for UAT
SE | 1 | 1 | 3 |  | 5 | Ready for UAT
SV |  |  |  | 2 | 2 | Ready for UAT
TR | 4 |  |  |  | 4 | Ready for UAT
VE | 2 | 1 | 1 |  | 4 | Ready for UAT
XC | 7 | 1 |  | 2 | 10 | Ready for UAT
GR | 7 | 1 | 2 |  | 10 | Ready for UAT
AT | 1 |  |  |  | 1 | Ready for UAT
Total | 52 | 8 | 25 | 10 | 95
Dev daily tracking
Count of # | Column Labels
Row Labels | 01 - Yet to start | 02 - In progress | 03 - Under review | 04 - Sent to eCase | 06 - Ready for QA | 07 - Blocked | 05 - eCase config completed | Grand Total
Prasanna | 10 |  | 2 |  | 11 | 1 | 4 | 28
Rathna | 1 | 1 |  | 1 | 19 | 3 |  | 25
Syed | 1 | 1 |  | 4 | 15 | 3 |  | 24
Vijay | 6 |  |  |  | 7 | 3 | 2 | 18
Grand Total | 18 | 2 | 2 | 5 | 52 | 10 | 6 | 95
Localization status
Count of # | Column Labels
Row Labels | 01 - Yet to start | 02 - In progress | 03 - Blocked | 03 - Completed | Grand Total |  |  |  | Loc
Prasanna | 13 | 11 | 1 | 3 | 28 |  |  |  | 01 - Yet to start
Rathna | 1 |  | 3 | 21 | 25 |  |  |  | 02 - In progress
Syed | 2 |  | 3 | 19 | 24 |  |  |  | 03 - Completed
Vijay | 14 |  | 3 | 1 | 18 |  |  |  | 03 - Blocked
Grand Total | 30 | 11 | 10 | 44 | 95

## W14 Status
# | Global Hold Code | Country Hold Code | Country Code | SIRG Code | SIRG ID | SIR Name | JSON | Complexity | Assignee | Hours (Portal) | Portal QA Hrs(Functionality except localization) | Components | Comments | Template Version | Config Status | Localization Status | QA Testing Template Version | QA status | Portal Team Target Date | Portal Delivered Date | eCase Team Target Date | Ecase Delivered Date | Localization Portal Target Date | FIT - QA/Testing | Work Comment
1 | VALU |  | HU | CPPY | ab097089-4df4-458e-ad53-a83553f51b67 | Proof of Payment - HU | 9f429d3c-19f9-4ad0-baff-7b8c58fd951a.json | Simple | Rathna | 1 | 2 | NA | only text change |  |  | 03 - Completed |  | 03 - Func. Testing completed
2 |  |  | HR | IRID | 91a372ee-50b6-4e4c-8952-167acaea87ea | Importer Registration ID - HR | 77382674-d4b5-46fc-b8a6-b7607416f310 | Medium | Vijay | 4 |  | Attributes : 2 Rule : 0 Liquibase Scripts : 2
3 |  |  | HR | DES | 98f5cf51-ac75-4461-a69f-48b211058bfc | Goods Description & HS Code - HR | ebf95dbb-e491-4d60-a341-be882d76183e | Simple | Bharti | 1 |  | Attributes : 1 Rule : 0 Liquibase Scripts : 0
4 |  |  | HR | ILIC | 6faf8993-4b7e-4054-b932-0417de638bc8 | Import License Required - HR | e05c777a-62a3-4800-af80-c2a61cd100c7 | Simple | Bharti | 1 |  | Attributes : 1 Rule : 0 Liquibase Scripts : 0
5 |  |  | HR | DIPL | 5070fa2c-f60a-44d0-82e3-0968ee295c06 | Diplomatic exemption - HR | New Json | Simple | Gaurish | 1 |  | Attributes : 1 Rule : 0 Liquibase Scripts : 0
6 |  |  | HR | CPPY | ab097089-4df4-458e-ad53-a83553f51b67 | Proof of Payment Document -Consignee - HR | New Json | Simple | Gaurish | 1 |  | Attributes : 1 Rule : 0 Liquibase Scripts : 0
7
8
9

## Localization
Country Code | Country Name | RTC number | Sent to Business | Received date | Update | Assignee | Country Localization (Static/Dynamic) Status | Status | Work comments | UAT readiness
GB | United Kingdom | 748756 |  |  |  | Prasanna |  |  |  | #VALUE!
TR | Turkey | 748757 |  |  |  | Vijay
SE | Sweden | 737680 |  |  |  | Rathna | Dynamic JSON completed | Completed
MM | Myanmar | 753929 |  |  |  | Prasanna | Dynamic Localization completed.
NZ | New Zealand | 753936 |  |  |  | Prasanna | Dynamic Localization completed.
AU | Australia | 753940 |  |  |  | Syed | No static JSON update. Completed dynamic JSON for 3 SIRG's. Remaining 3 are in blocked status.
ID | Indonesia | 753944 |  |  |  | Rathna | Dynamic JSON completed | Completed
CR | Costa Rica | 753960 |  |  |  | Rathna | Dynamic JSON completed | Completed
BO | Bolivia | 753971 |  |  |  | Syed | No static JSON update.. Completed dynamic JSON. | Completed | Dynamic text changes done.
VE | Venezuela | 754512 |  |  |  | Prasanna | Dynamic Localization completed.
XC | Curacao | 755509 |  |  |  | Prasanna
DO | Dominican Republic | 755560 |  |  |  | Vijay
CL | Chile | 755616 |  |  |  | Prasanna | Dynamic Localization completed.
MA | Morocco | 755640 |  |  |  | Vijay
JO | Jordan | 755793 |  |  |  | Syed | Dynamic Localization completed. |  | General UI labels/error messages for static JSON creation are yet to be finalized. Dynamic localization completed as per template v1.1.
SV | El Salvador | 755796 |  |  |  | Rathna
GR | Greece | 758035 |  |  |  | Syed | Static Localization Completed.
AT | Austria | 619799 |  |  |  | Rathna

## W13 Timelines
Wave 13 Plan [Without code changes]
Activity | Start date | End date |  | Key callouts
SIR requirement submitted last date | 2023-03-13 | 2023-03-29 | 13 | - Wave 13 timelines have been extended by 1week. Main reason is addition of GR 10 SIRs. - No open cases expected in PROD that uses old generalized SIR config. - Existing SIRGs for CL - PII, 2 versions of SIRGs will be maintained to support any open cases. - 27 DocFamily/DocType are not present in GIA. Based on discussion with Aditya config team will proceed with ENT/ENT for Wave 13. New DocFamily/DocType requires code changes hence not part of Wave 13. - No structural CRs will be accepted during UAT. - No localization changes after 1st week of UAT will be accepted
Understanding the templates/Clarifications/estimation | 2023-03-13 | 2023-03-30 | 14
SIRG set-up in portal | 2023-03-27 | 2023-05-12 | 35
SIRG set-up in eCase | 2023-03-29 | 2023-05-17 | 36 | Important Deadlines for Business to Provide the details: - SIR Submission Deadline: 29th March - Text changes Deadline: 26th May - File Template Changes + SIR Structure Changes: 5th April
SIT | 2023-04-03 | 2023-05-19 | 35
UAT | 2023-05-22 | 2023-06-02 | 10
Regression Testing [any text change/bug fixes] | 2023-06-05 | 2023-06-09 | 5
Soft RTP/Fortify scan/TAT | 2023-06-07 | 2023-06-09 | 3
RTP | 2023-06-11 | 2023-06-11 | 0
Hyper care support | 2023-06-12 | 2023-06-16 | 5
0
0
0
0
0
0
0
0
0
0
Formulas:
Start date = [Start date, row above]
Start date = [Start date, row above]+2
End date = [Start date]+46
End date = [End date, row above]+5

## Defect_Tracker
S.No | Defect/CR | Summary | Owned By | Status | ETA
1 | 749447 | Notification Date Column sub header format is incorrect for SE - Expected YYYY-MM-DD is shown Actual dd-mm-yyyy - English | Syed | Completed
2 | 748148 | CR: IL - FDA B2B Description Text updates | Prasanna | Inprogress |  | Raised PR for the defect, waiting for deployment.
3 | 750254 | PA ACHR - Submit button is enabled without selecting any values in Portal UI | Prasanna | Inprogress |  | As per the requirement, made the changes in JSON file and hand over to Senthil.
4 | 762290 | BB-POA Input Text box description is missing in Portal
5 | 763295 | AU - ICTC - eCase sub status still shows Customer Contacted after case submission | Priyanka Shetty | Fixed
W12 Backlog items:
Defect
1 | 753949
2 | 749694
3 | 748734
4 | 748305
5 | 748148
6 | 748144
7 | 747258

## Daily_Tracker (hidden)
Date | 27th March
Total SIR | 82
Ecase completed | 0
Customer portal set-up completed | 2
SIR work in progress | 11
SIR not started (includes SIR need to be code change ) | 69
Total Countries | 17
Received from business | 16
Sent to Business | 0
Localization completed | 0
Localization work in progress | 0
Localization not started | 0
Testing Completed (Including SIR Localization ) | 0
Testing Completed (excludes SIR Localization ) | 0
Total Open Defects | 0
Localization Open Defects | 0
Open CR's | 0
SIR Open Defects | 0
Note

## Doc Type Open Item
Country Code | SIRG | DocFamily | DocType | Sub Type | GIA supported? | Wave 13 Doc Family | Wave 13 Doc Type
MM | MED | PDC | PPL |  | Not a doctype in GIA | PDC | PMD | Row Labels | Count of Country Code
NZ | PERS | PDC | PFX |  | Not a doctype in GIA | PII | NID | CA | 10
AU | PERS | PDC | PFX |  | Not a doctype in GIA | PII | NID | ADA | 10
AU | RGR | ENT | RNR |  | Not a doctype in GIA | ENT | ENT | CCD | 8
TR | RGR | ENT | RNR |  | Not a doctype in GIA | ENT | ENT | PLI | 8
TR | TXXM | ENT | RNR |  | Not a doctype in GIA | ENT | ENT | ENT | 4
XC | ZOOT_PHYT | PDC | PPL |  | Not a doctype in GIA | ENT | ENT | EXP | 1
CL | PERS | CA | ADA | ECI | Yes but not for GCCP | ENT | ENT | RNR | 3
CL | TXXM | CA | ADA | ECI | Yes but not for GCCP | ENT | ENT | PDC | 5
CL | DIPL | CA | ADA | ECI | Yes but not for GCCP | ENT | ENT | PFX | 3
CL | RGR | CA | ADA | ECI | Yes but not for GCCP | ENT | ENT | PPL | 2
CL | REXP | CA | ADA | ECI | Yes but not for GCCP | ENT | ENT | PPW | 8
DO | PHYT | CCD | PLI |  | Yes but not for GCCP | ENT | ENT | INV | 6
DO | CER | CCD | PLI |  | Yes but not for GCCP | ENT | ENT | PKL | 2
DO | IRID | CA | ADA | ECI | Yes but not for GCCP | ENT | ENT | Grand Total | 35
DO | MED | CCD | PLI |  | Yes but not for GCCP | ENT | ENT
DO | DRUG | CCD | PLI |  | Yes but not for GCCP | ENT | ENT
DO | DRUG | CA | ADA | ECI | Yes but not for GCCP | ENT | ENT
XC | ELEC | CCD | PLI |  | Yes but not for GCCP | ENT | ENT | Next steps
VE | CER | CCD | PLI |  | Yes but not for GCCP | ENT | ENT | Once decided by EA/DA finalize the DocType/Family
VE | ILIC | CCD | PLI |  | Yes but not for GCCP | ENT | ENT | Request to GIA. GIA will first implement
TR | REXM | CA | ADA | ECI | Yes but not for GCCP | ENT | ENT | ESB Service
TR | RGR | CA | ADA | ECI | Yes but not for GCCP | ENT | ENT
TR | TXXM | CA | ADA | ECI | Yes but not for GCCP | ENT | ENT
CR | ZOOT_PHYT | CCD | PLI |  | Yes but not for GCCP | ENT | ENT
GR | AUTH | PPW | PKL |  | Not a doctype in GIA | ENT | ENT
GR | AUTH | PPW | INV |  | Not a doctype in GIA | ENT | ENT
GR | REXP | ENT | EXP |  | Not a doctype in GIA | ENT | ENT
GR | CPC | PPW | PKL |  | Not a doctype in GIA | ENT | ENT
XC | INV | PPW | INV |  | Yes but not for GCCP | ENT | ENT | Yes but not for GCCP > Mostly ESB config. These could be developed.
XC | MED | PPW | INV |  | Yes but not for GCCP | ENT | ENT | What are the important doc types…can we get the BCRS for that first?
XC | FOOD | PPW | INV |  | Yes but not for GCCP | ENT | ENT
XC | ZOOT_PHYT | PPW | INV |  | Yes but not for GCCP | ENT | ENT | Keeping the doc type configurable
XC | AGLS | PPW | INV |  | Yes but not for GCCP | ENT | ENT | Based on the doctype, attributes to be sent to GIA will change
XC | DUXM | PPW | INV |  | Yes but not for GCCP | ENT | ENT | 100% configurability is not possible. But common framework can be made and reduce the repetitive effort which will cover aroun 60-70%
MM | PII | PDC | PFX |  | Not a doctype in GIA | PII | NID
GB | PERS | PDC | PFX |  | Not a doctype in GIA | PII | NID
DO | PERS | PDC | PFX |  | Not a doctype in GIA | PII | NID
Row Labels
AU
PERS
RGR
CL
PERS
CL
DIPL
REXP
RGR
TXXM
CR
ZOOT_PHYT
DO
CER
DRUG
IRID
MED
PHYT
GR
AUTH
CPC
REXP
MM
MED
PII
NZ
PERS
TR
REXM
RGR
TXXM
VE
CER
ILIC
XC
AGLS
DUXM
ELEC
FOOD
INV
MED
ZOOT_PHYT
Grand Total

## Liquibase_scripts
# | SIRG | Country Code | Lang | Form Name | File Path | Assignee | Status | Target Date
1 | FTZ | ID | en | FTZ_Kode_Barang_Template |  | Rathna | Completed
2 | PERS | AU | en |  |  | Syed | Blocked
3 | COO | AU | en | MANF_DECL_FORM |  | Syed | Completed
4 | CPOA | JO | en | Auth_Letter_Form |  | Syed | Completed
5 | CPOA | AR | ar | Auth_Letter_Form |  | Syed | Completed
6 | ZOOT_PHYT | CR | es | Permit_App_Letter |  | Rathna | Completed
7 | ZOOT_PHYT | CR | es | Auth_Doc |  | Rathna | Completed
8 | PERS | NZ | es |  |  | Prasanna | InProgress
9 | PERS | NZ | es |  |  | Prasanna | InProgress
10 | PII | MM |  |  |  | Prasanna | Not Started
11 | IRID | CR | es | ILRQ_Manual_Reg |  | Rathna | Completed
12 | DOV | CL | es | Affidavit |  | Prasanna | Not Started
13 | POA | MA | fr | Auth_Letter_Doc |  | Syed | Completed
14 | POA | GR | el | ISISNET_GUIDE |  | Rathna | Completed

## Risk Log
Sr No. | Type | Description | Mitigation / Resolution | Status | Severity | ETA | Start Date | Resolution Date
1 | Templates analasis | ONB team need to understand the Shared templates and need to check the config/code changes | If its code changes need to effort the estimations asap | Closed |  |  | 13th March | 30th March
2 | timelines Freeze | onb team is not able to freeze the wave 13 time lines due to use cases are subimitting after cut of date | Discussing with the business to Freeze the use case submission | Closed |  |  | 13th March | 29th march
3 | Doctype | Few doctypes is not present in GIA | Aditya has shared the doc fmaily and doc type detials to proceed the configuraitons,but still 11 items having blocked due to the same | In progress | High |  | 3rd April | 18th April 2023
4 | Xpath clarifications | ONB team need few clarificaitons from vignesh/senthil to proceed configuraiton of xpath related things for few SIRG'S | onb team has received few details for couple SIRG'S rest ITS team is checking with architect team | In progress | High |  | 10th April | 28th April

## Lang_Map
S.NO | New/Existing | Full Name | Country | Languages | Default Language | P/F | SMS/Email Notificaton
1 | Existing | United Kingdom | GB | English | English
2 | Existing | Turkey | TR | Turkish, English | Turkish
3 | Existing | Sweden | SE | English, Swedish | Swedish
4 | Existing | Myanmar | MM | English | English
5 | Existing | New Zealand | NZ | English | English
6 | Existing | Australia | AU | English | English
7 | Existing | Indonesia | ID | English, Indonesian | Indonesian
8 | Existing | Costa Rica | CR | English,Spanish | Spanish
9 | Existing | Bolivia | BO | English, Spanish | Spanish
10 | Existing | Venezuela | VE | English, Spanish | Spanish
11 | New | Curacao | XC | English, Spanish | English | Fail | ODD default language is pending from Business
12 | Existing | Dominican Republic | DO | English, Spanish | Spanish
13 | Existing | Chile | CL | English, Spanish | Spanish
14 | New | Morocco | MA | English,French | French | Fail | ODD default language is pending from Business
15 | New | Jordan | JO | English,Arabic | Arabic | Fail | ODD default language is pending from Business
16 | Existing | El Salvador | SV | English, Spanish | Spanish
17 | New | Greece | GR | English.Greek | Greek | Fail | ODD default language is pending from Business
18 | Existing | Austria | AT | English,German | German
19 | Existing_Backlog | Barbados | BB | English | English
20 | Existing_Backlog | Hungary | HU | Hungarian, English | English | Pass
21 | Existing_Backlog | Israel | IL | Hebrew,English | Hebrew | Pass

## RTP_Dates (hidden)
April RTP with Clearence Integrations Deadline details
Item | Start date | End date
SIR set-up in portal
SIT
UAT
Regression Testing
RTP
Go Live + HYP

## Attributes & Confluence
Country Code | Assignee | Attribute Status | Confluence Status

## xPath Open Item
Country Code | SIRG/Description | Attributes | XPATH | Comments (Can we use below xpath's?) | Status | Note:
AU | RGR | Value of the Original Goods |  | ShpPcdDetailsMsg/Bd/Shp/MonAmt/Amt/@TyCd=TCUSV | Completed | Mentioned SIRG's are on hold until xPath clarification is completed
HR | DIPL | IOU document Uploader |  |  | Open
HR | CPPY | Node textfield |  |  | Open

## SIRG modification
S.NO | Country Code | SIRG | Remarks
1 | DO | POA | Existing case will be cancelled due to low Volume
2 | CL | PII | Maintain 2 version of JSON
3 | CL | PERS | Existing case will be cancelled due to low Volume
4 | SE | DUXM | Ecase to apply patch for existing cases mapped to DEXM
5 | BB | DUXM | Ecase to apply patch for existing cases mapped to DEXM